## Status Report
Project Name | Kashti 2.0 |  | Date |  | 2020-10-10 | Project Manager |  | Cody Uhi
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a web-based User Interface (UI) that offers full functionality for the Brigade event-driven scripting platform by the end of April 2021. |  |  |  | Create Low-Fidelity Prototype for UI |  | 0% | Possible Delays |  | 2020-10-16
|  |  |  | Research Angular vulnerabilities |  | 25% | On Track |  | 2020-10-21
|  |  |  | Research Kubernetes Implementations |  | 25% | On Track |  | 2020-10-14
|  |  |  | Research Angular Framework |  | 0% | On Track |  | 2020-10-21
|  |  |  | Research Brigade Implementations |  | 0% | On Track |  | 2020-10-21
|  |  |  | Complete Project Definition Document |  | 100% | Complete |  | 2020-10-17
|  |  |  | Prove communication and team resources are available to team |  | 100% | Complete |  | 2020-10-05
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Confirm all communication channels and resources are available to everyone in the team. Complete and review the Project Definition Document. |  |  | Begin work on design for a low-fidelity prototype |  |  | Make a list of vulnerabilities associated with the Angular JS Frontend Framework. Complete familiarization with Kubernetes technology. Developers perform research on Angular JS Framework for familiarization.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Derryck Dunn | Backend/Existing Implementation | 6 | Issue | Unable to meet with the design expert sponsor this week, delaying the start of the design work on the project.
Cody Uhi | PM/Designer. Prepared meeting agendas, collaborated team activity, and completed the Project Definition Document. | 7
Daniel De La O | Research Angular Framework, begin design process | 6
Spencer Sundrud | Vulnerability research | 6 | Risk | Starting on the design process too late will prevent the team from being able to start building the product on the correct timeline.
Stephen Kendall | Learning brig & kubernetes | 5
|  |  | Issue | The team currently is not tracking progress on research endeavors very well. We need to address this either by standardizing our research efforts based on technologies or by being clearer in the resources we are using so everyone can pool their knowledge/learning.
Total |  | 30

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task