## Status Report
Project Name | Kashti 2.0 |  | Date |  | 2020-10-17 | Project Manager |  | Cody Uhi
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a web-based User Interface (UI) that offers full functionality for the Brigade event-driven scripting platform by the end of April 2021. |  |  |  | Create Low-Fidelity Prototype for UI |  | 100% | Complete |  | 2020-10-16
|  |  |  | Research Angular vulnerabilities |  | 75% | On Track |  | 2020-10-21
|  |  |  | Research Kubernetes Implementations |  | 75% | On Track |  | 2020-10-14
|  |  |  | Research Angular Framework |  | 75% | On Track |  | 2020-10-21
|  |  |  | Research Brigade Implementations |  | 75% | On Track |  | 2020-10-21
|  |  |  | Complete System Lvl Heuristic Document |  | 100% | Complete |  | 2020-10-23
|  |  |  | Prepare the 3 min. Presentation |  | 100% | Complete |  | 2020-10-05
|  |  |  | Create a LucidChart documentation for API |  | 60% | Future Task |  | 2020-10-19
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Complete the System level heuristic document. Create a low-fidelity prototype for the UI. Prepare a 3 minute presentation for the class. |  |  | n/a |  |  | Perform research regarding Angular vulnerabilities, Angular usage, Brigade 2.0 usage, Perform a 3 minute presentation to the class about our project. Create a LucidChart documentation for the Brigade API interactions.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Derryck Dunn | Research, establishing visuals for API calls visual through Lucid Chart for easier understanding, meetings | 7 | Issue | We do not know the answer to the question "when do we start coding?"
Cody Uhi | Research Angular, define the lo-fi prototype, complete system lvl heuristic document, prepare 3 min presentation | 10
Daniel De La O | Research on UX and UI, create documents | 8
Spencer Sundrud | Research, presentation preparation | 7 | Risk | We have invested in a lot of hours in researching but have not proven that the research has viability yet because we haven't built anything.
Stephen Kendall | Learning brig, k8s, UI prototypes | 9
|  |  | Issue | n/a
Total |  | 41

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task