## Status Report
Project Name | Kashti 2.0 |  | Date |  | 2020-10-23 | Project Manager |  | Cody Uhi
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a secure, interactive web-based User Interface (UI) that offers full functionality for the Brigade event-driven scripting platform by May 2021. |  |  |  | Research Angular Vulnerabilities |  | 100% | Complete
|  |  |  | Research Kubernetes Implementations |  | 100% | Complete
|  |  |  | Research Angular Framework |  | 100% | Complete
|  |  |  | Research Brigade Implementations |  | 100% | Complete
|  |  |  | Prepare/perform 3 min. Presentation |  | 100% | Complete
|  |  |  | Build a login page/proof-of-concept |  | 5% | On Track
|  |  |  | Prepare/perform vulnerabilities Presentation |  | 100% | Complete
|  |  |  | Build a TypeScript SDK for Brigade |  | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Initial research endeavors have been completed (Angular, TypeScript, Brigade implementations, Kubernetes). A 3 minute presentation was prepared and given in class describing our project. |  |  | None at thsi time. |  |  | Build a login page/proof-of-concept. Build a TypeScript SDK.
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Cody Uhi | Prepare/present 3 min presentation. Research Angular. Prepare development environment/planning resources. | 8 | Issue | Some of the Key Tasks are monolithic and it will be harder to track day-to-day progress on them. This should be more strongly segmented.
Derryck Dunn | Lucidchart visual on API/ SDK and learning typescript in preparation for SDK construction. | 7
Daniel De La O | Meetings with Kent and Building desired features | 8
Spencer Sundrud | Vulnerabilities research, OpenID Connect research, vulnerabilities presentation | 7 | Issue | We do not have a strong timeline to follow for smaller tasks within the Key Tasks. This ambiguity makes it less likely for work to be done on them, as students would rather focus their time on other assignments that DO have defined due dates.
Stephen Kendall | Learning Typescript & SDK | 5
|  |  | Issue | We have not done much coding work together so far and we still need to get used to others' work style. If this does not start soon we will not be able to address it until later.
Total |  | 35

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task