## Status Report
Project Name | Kashti 2.0 |  | Date |  | 2020-11-06 | Project Manager |  | Cody Uhi
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a secure, interactive web-based User Interface (UI) that offers full functionality for the Brigade event-driven scripting platform by May 2021. |  |  |  | Build hi-fi prototype |  | 10% | On Track
|  |  |  | Create MVP for typescript SDK |  | 10% | Possible Delays
|  |  |  | Individuals list challenges the project is facing |  | 0% | On Track
|  |  |  | Create a 3-minute presentation for the class |  | 5% | On Track
|  |  |  | Complete peer evaluations |  | 20% | On Track
|  |  |  | Build OIDC proof of concept |  | 100% | Complete
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
OIDC proof of concept built Charted structure of authx section in the SDK | [5 empty] | Everyone individually list the challenges that they feel the project is facing. Build a hi-fidelity prototype using code to present on Monday (11-9-20) Create a MVP for the typescript SDK with basic GET, POST, PUT/PATCH, and DELETE functionality Create a 3 minute presentation for class
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Cody Uhi | Completed the OIDC proof of concept app, began powerpoints for the end of semester and 3 minute presentations, re-strategized efforts to meet closer deadlines | 6 | Issue | Time to meet as group and have consistent progress in key areas
Derryck Dunn | In the process of working through final visuals for the structure of the project, so that me and Steven can meet to begin typesrcipting the SDK for V2.0. | 7
Daniel De La O | Start UI prototype | 6
Spencer Sundrud | Building sample Angular app to test OpenID Connect | 6 | Issue | Understanding backend functionality enough to integrate it into the frontend.
Stephen Kendall | Charting SDK structure | 7
|  |  | Risk | As we continue to make progress in our general understanding and coding of the project, we could still find oursleves with questions and needing more time to understand the content. Essentially, we could run the risk of spending more time than we think we need. The best approach is to make sure we measure and evaluate along the way, so that we can be prepared and organized come any deadlines.
Total |  | 32

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task