## Status Report
Project Name | Kashti 2.0 |  | Date |  | 2020-11-14 | Project Manager |  | Cody Uhi
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a secure, interactive web-based User Interface (UI) that offers full functionality for the Brigade event-driven scripting platform by May 2021. |  |  |  | Ui prototype with css assets |  | 80% | On Track
|  |  |  | Create MVP for typescript SDK |  | 15% | Possible Delays
|  |  |  | Create a 3-minute presentation for the class |  | 7% | On Track
|  |  |  | Completing the core graphing portion of the SDK |  | 60% | On Track
|  |  |  | Individuals list challenges the project is facing |  | 100% | Complete
|  |  |  | Complete peer evaluations |  | 100% | Complete
|  |  |  | Brigade Authentication |  | 60% | On Track
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Peer evaluations Individuals list challenges the project is facing Complete peer evaluations | [5 empty] | Successful Brigade authentication Create a 3-minute presentation for class
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Cody Uhi | Meet with SDK team and create strategy for building SDK, meet with UI team and create strategy for building UI | 8 | Risk | We have multiple tasks that need to be completed, and some of those tasks are taking longer to complete than we previously thought
Derryck Dunn | Mapping with team members in order to further understand SDK functionality, as well as working to complete mapping out the core portion in preparation for both typescripting and next week's presentation. | 6
Daniel De La O | Create a prototype with assets | 7
Spencer Sundrud | Setting up Brigade authentication, testing local storage vulnerabilities | 6 | Issue | With Thanksgiving break approaching, many of us are having to prioritize some of our other classes with respect to projects and exams. Meaning, less time to work on the project come these next few weeks.
Stephen Kendall | Working on strategy & charting for the SDK | 5
Total |  | 32

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task