## Status Report
Project Name | Kashti 2.0 |  | Date |  | 2020-10-30 | Project Manager |  | Cody Uhi
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a secure, interactive web-based User Interface (UI) that offers full functionality for the Brigade event-driven scripting platform by May 2021. |  |  |  | Verify everyone can contribute to the repository |  | 100% | Complete
|  |  |  | Create a MVP for the TypeScript SDK |  | 15% | Possible Delays
|  |  |  | OIDC integration with Angular Proof-of-concept |  | 15% | Possible Delays
|  |  |  | Break down the Go SDK |  | 50% | On Track
|  |  |  | Make a list of features to be transferred to the TypeScript SDK |  | 100% | Complete
|  |  |  | Re-establish expectations with sponsors |  | 0% | Future Task
|  |  |  | n/a |  | 0% | Future Task
|  |  |  | n/a |  | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Peer programming meetings attended OIDC integration with Angular Proof-of-concept started Began breaking down the Go SDK Made a list of features the Go SDK has to see if we want them in the typescript SDK |  |  | Possible delays on OIDC Proof of Concept due to lack of progress Possible delays on TypeScript SDK due to lack of progress ^Reality of these delays depend on expectations of where our progress should be |  |  | Complete the Proof-of-concept for OIDC Establish a minimum-viable-product for the Typescript SDK
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Cody Uhi | Started work on OIDC integration into an angular app, planned for meetings/peer programming | 6 | Issue | The team is currently experiencing low morale/burnout due to large workload present in other classes/work. We need to find a way to motivate ourselves to work on the project.
Derryck Dunn | Began trying to devour the SDK code in the git hub repo. I've also had a chance to meet with Stephen to coordinate and generate a list of questions to ask the spo)nsors on Monday, with respect to test files and certain portions of the code they wish or not wish to keep goin forward for the 2.0 version. Additionally, I have had a chance to view a YouTube video that summarizes how go works if you have a C language mentality. This will hopefully help us to understand and build version 2.0 going forward. | 7
Daniel De La O | Set up personal git work on writting angular | 5
Spencer Sundrud | Angular Vulnerabilities finished research and presentation, research OpenID Connect implementation code | 6 | Issue | The project has multiple parts to it and our team does not know where it should should be on these parts of the project. We need to talk to the sponsors about where they expect us to be on each part of the project so we know whether we are focusing on the correct things at the correct times.
Stephen Kendall | Learning Go SDK | 6
|  |  | Issue | Due to the multiple parts of the project, it is hard to gauge progress on those parts of the project. We need to find a way to organize everything that is going on.
Total |  | 30

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task