## Status Report
Project Name | Kashti 2.0 |  | Date |  | 2020-11-21 | Project Manager |  | Cody Uhi
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a secure, interactive web-based User Interface (UI) that offers full functionality for the Brigade event-driven scripting platform by May 2021. |  |  |  | UI demo for presentation |  | 70% | On Track
|  |  |  | Create MVP for typescript SDK |  | 15% | Possible Delays
|  |  |  | Create a 3-minute presentation for the class |  | 100% | Complete
|  |  |  | Completing the core graphing portion of the SDK |  | 100% | Complete
|  |  |  | Brigade Authentication |  | 80% | On Track
|  |  |  | Write a self-reflection of the project |  | 40% | On Track
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Presentation given Receive mentorship from sponsors Build architectural diagrams for SDK |  |  | Progress on the SDK |  |  | Finish the visual prototype Complete Authentication Work on the SDK
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Cody Uhi | Created/gave presentation, coordinated SDK work, received mentorship from sponsors about building SDK, began building SDK | 13 | Issue | As per armour, we don't know what we don't know about the project yet because we still need to perfom significant work on it.
Derryck Dunn | Finalizing the structure of the SDK through charting, meeting with the sponsors to begin and uderstand the typescripting process, and begining to establish the skeletal structure for better SDK undertsanding. | 10
Daniel De La O | Polish the UI and meet with Ronan to get feedback | 10
Spencer Sundrud | Security information for group presentation, brigade authentication research/coding | 10 | Issue | Organization/work process for the SDK is not well defined. How do we most efficiently work on this single thing with multiple people working at once?
Stephen Kendall | Charted SDK; coordinated plan for writing in typescript | 8
|  |  | Issue | There is a level of expertise that exists among team members, but the knowledge gap between different areas of the project mean that either team members need to collaborate better or receive training/skill in other areas of the project.
Total |  | 51

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task